**Annex C: Payment Table**

|  |  |  |
| --- | --- | --- |
| **Milestone** | **Amount** | **Date** |
| **Milestone #1 (M1)**: Project document signature | US$ XX | **Month 1** |
| **Milestone #2 (M2) Observation**: Please indicate a substantive, punctual, tangible and observable activity  e.g., Completion of the 30th Training of Trainers (TOT) program in 5 project districts. (Output 1.2)  **Deliverable due:** Please indicate a deliverable to be shared at completion of the milestone  e.g., Training manual, PowerPoint presentations or other. | US$ XX | **Month 8**  In the Work Plan (Annex II), the activity must be timed to take place during Month 8 |
| Milestone #3 (M3) Observation: Please indicate a substantive, punctual, tangible and observable activity  e.g., Completion of the 40th Linkage workshop in 5 project districts. (Output 2.2)  Deliverable due: Please indicate a deliverable to be shared at completion of the milestone  e.g., Workshop report, photos, list of participants or other. | US$ XX | **Month 16**  In the Work Plan (Annex II), the activity must be timed to take place during Month 16 |