UN-OHRLLS

RoadMap for the Implementation of the

Istanbul Programme of Action from 2011 to the Mid-Term review

Introduction

The Fourth United Nations Conference on LDCs adopted the Istanbul Declaration and the Istanbul Programme of Action for the decade 2011-2020 (IPoA). The IPoA takes the form of a mutually agreed compact between LDCs and their development partners and contains eight priority areas of action, each supported by concrete deliverables and commitments. These eight development priorities include productive capacity, agriculture, food security and rural development, trade, commodities, human and social development, multiple crises and other emerging challenges, mobilizing financial resources for development and capacity- building, and governance at all levels. An emphasis is placed on equity at all levels through empowering the poor and marginalized, and ensuring  social justice, democracy, gender equality and sustained, inclusive and equitable economic growth and sustainable development.

With the adoption of such a comprehensive and result-oriented Programme of Action, the new and challenging phase ahead is one of ensuring that the deliverables and commitments in favour of LDCs lead to concrete actions. Cognizant of the need not to loose the momentum built in the wake of the successful conclusion of the Fourth United Nations Conference on LDCs, a Roadmap has been developed to ensure a swift move towards the implementation phase of the newly adopted Programme of Action.  Seen as a planning tool, the roadmap is designed for the purpose of steering the LDCs and their development partners on a path of a coordinated, coherent and effective and gender sensitive implementation of the IPoA.

The Roadmap provides for concise insight into the:

- The different vehicles/actors that will be used in order to accelerate the implementation of the IPoA (Intergovernmental machinery, UN system and other international organizations and regional banks, Global Partnerships, South-South Cooperation and Multistakeholder Engagement );

- The objectives  which the above vehicles/actors will help arrive at;

The activities/steps, including the substantive ones, which need to be deployed in order to deliver the expected outcomes.

Road Map for the Implementation of the Istanbul Programme of Action from 2011 to the Mid-Term review

|  | Objectives | Activities to be undertaken | Target dates for action | Responsible intergovernmental bodies, agencies and other entities |
| --- | --- | --- | --- | --- |
| Intergovernmental Cluster | Global | Promoting global consensus building in support of the implementation of the IPoA | General Assembly annual reviews of the implementation of the Istanbul Programme of Action and GA resolutions in support of the implementation of the Istanbul Programme of Action; | Starting from September 2011 up to the mid-term review of the IPoA | GA, OHRLLS, DGACM and other UN system organizations |
|  |  |  | ECOSOC annual reviews of the implementation of the Programme of Action, including through mechanisms such as AMR and Development Cooperation Forum, resolutions in support of the implementation of the Programme of Action. | Starting from July 2011 up to the mid-term review of the IPoA | ECOSOC, OHRLLS, DESA and ECA |
|  |  |  | Periodic reviews by the Trade and Development Board of the implementation of the Istanbul Programme of Action, with a focus on substantive issues addressed in the LDC Report as well as technical support extended to the LDCs | Starting from June 2011 up to the mid-term review of the IPoA | TDB, UNCTAD |
|  |  |  | Active participation in and substantive contribution to the preparatory process of and to major UN Conferences and other International Conferences and Initiatives, e.g Rio+20, AfT Global Review, Busan Conference on Aid Effectiveness, the High-Level Committee on South South Cooperation, DCF, G-20, UNCTAD XIII, etc... | Starting from June 2011 up to the mid-term review of the IPoA | LDC Global Bureau, OHRLLS and other UN system organizations |
|  |  |  | Active participation in and substantive contribution to the final review of the MDGs and its follow-up | Starting from June 2011 up to the mid-term review of the IPoA | LDC Global Bureau, OHRLLS and other UN system organizations |
|  |  |  | LDC Ministerial Meetings | The first will be held in September 2011 and the periodicity of the remaining meetings to be determined at the September meeting | LDC Global Bureau and OHRLLS |
|  |  | Follow up, monitoring and review of the Istanbul Programme of Action | Endorsement of the Istanbul Programme of Action by the GA | Jun-11 | GA |
|  |  |  | Report of the SG on the outcome of the Istanbul Conference | Jun-11 | OHRLLS |
|  |  |  | Publish the list of deliverables | Jul-11 | OHRLLS with substantive inputs of UN system organizations, the BWIs and other international organizations |
|  |  |  | Annual reports of the Secretary-General on the implementation of the IPoA | These recurrent reports are due in May of every year | OHRLLS with substantive inputs of UN system organizations |
|  |  |  | Establishment by the General Assembly of ad-hoc working group on smooth transition and support the work of the ad-hoc working group | December 2011 and after | GA, with the support of OHRLLS, DESA |
|  |  |  |  |  | and UNCTAD |
|  |  |  | Report on smooth transition strategies as per GA/RES/65/171 | May-12 | DESA, OHRLLS, UNCTAD with inputs from member states |
|  |  |  | Global mid-term review of the IPoA | 2015 (TBC) | OHRLLS, with substantive inputs from all stakeholders |
|  | Regional | Promoting regional consensus building in support of the implementation of the IPoA | Establishment of the biannual agenda item, decision to mainstream the IPOA into the work programme of the commissions, Biennial review of the implementation of the Istanbul Programme of Action at the regional and sub-regional level by the Regional commiss | Starting from November 2011 | Regional Commissions (ECA and its sub-regional offices (SROs), ECLAC, ESCAP and ESCWA) and OHRLLS |
|  | National | Mainstreaming the IPoA into LDCs’ national development plans and strategies | Maintain and further strengthen cooperation between OHRLLS and LDCs on the implementation of the Istanbul Programme of Action | Starting from June 2011 up to the mid-term review of the IPoA | OHRLLS and LDCs |
|  |  |  | Prepare a Memorandum of Understanding between OHRLLS and UNDG, with UNDP acting as Chair of UNDG. This memorandum will guide the efforts of all UN system organizations in supporting national-level mainstreaming and implementation of the IPoA, including t | Between July 2011-October 2011 | OHRLLS and UNDP, as chair of UNDG, and UN system organizations with a field presence |
|  |  |  | Formulate a detailed project proposal on national-level mainstreaming of the IPoA. The project will help identify approaches to mainstream the IPoA into national development strategies. It will also help identify ways in which UN country teams could come | Between October 2011-December 2011 | OHRLLS,UNDG, UNCTAD,ECA, ESCAP and UN system organizations with a field presence |
|  |  |  | Seek funding for the project | Between Jan 2012-March 2012 | OHRLLS and UNDP, ECA, ESCAP and UN system organizations with a field presence |
|  |  |  | Workshop of National Focal Points. The national focal points are LDC government officials dealing with the LDC-related issues and stationed in their respective capitals. | July of every year from 2012 | OHRLLS |
|  |  |  | Implementation of other activities of the project | From May 2012-April 2015 | OHRLLS, UN Country Resident Coordinators, ECA, ESCAP and UN system organizations with a field presence |
|  |  | Mainstreaming the IPoA into donor countries and emerging countries' development cooperation strategies | Maintain and further strengthen cooperation between OHRLLS and donor countries and emerging countries on the implementation of the Istanbul Programme of Action | Starting from June 2011 up to the mid-term review of the IPoA | OHRLLS, donor countries and emerging countries |
|  |  |  | Encourage donor countries and emerging countries to develop donor strategies to support the effective implementation of the Istanbul Programme of Action | Starting from June 2011 up to the mid-term review of the IPoA | OHRLLS, OECD/DAC and UNCTAD and donor countries and emerging countries |

|  | Objectives | Activities to be undertaken | Target dates for action | Responsible intergovernmental bodies, agencies and other entities |
| --- | --- | --- | --- | --- |
| The UN System, the BWIs, and Other International Organizations | Mainstreaming the IPoA into the work programmes of UN Funds, Programmes and specialized agencies | Maintain and further strengthen cooperation between OHRLLS and UN Funds, Programmes and specialized agencies on the implementation of the Istanbul Programme of Action | Starting from June 2011 up to the mid-term review of the IPoA | Member states, with the support of OHRLLS and UN Funds, Programmes and specialized agencies |
|  |  | Decision adopted by the Executive Board of UNICEF inviting UNICEF to integrate the IPoA into its programme | Jun-11 | UNICEF |
|  |  | Decision adopted by the Executive Board of WFP to integrate the IPoA into its programme | Nov-11 | WFP |
|  |  | Decision adopted by the Executive Board of UNDP, UNFPA and UNOPS inviting these institutions to integrate the implementation of the Istanbul Programme of Action into their programmes of works, including the programme of work of UNCDF | Jun-11 | UNDP, UNFPA and UNOPS, UNCDF |
|  |  | Discussion on the implementation of the Istanbul Programme of Action to be held in the joint meeting of Executive Boards of UNDP, UNFPA, UNICEF, UN-Women and WFP inviting these funds and programmes to mainstream the IPoA into their work programmes | Feb-12 | UNDP, UNICEF, UNFPA, UN Women and WFP |
|  |  | Decision to be taken by the Executive Board of UN Women requesting the Executive Director to integrate the implementation of the Istanbul Programme of Action in the activities of UN-Women in accordance with its mandate | Jun-11 | UN Women |
|  |  | Follow-up, through HLCP, of the CEB decision of Spring 2011 to build on the outcome of the Conference and UN system support to the mainstreaming of the IPoA | HLCP 22nd Session in September 2011 | OHRLLS |
|  |  | Engagement with the SG's Policy Committee with the view of contributing to the considering of LDC development agenda in the discussions within and deliberations of the Committee | Starting from June 2011 | OHRLLS |
|  |  | Follow-up, through UNDG, of the CEB decision of Spring 2011 to build on the outcome of the Conference and UN system support to the operational mainstreaming of the IPoA | Starting from June 2011 | OHRLLS, UNDG , with the support of UN system organizations |
|  |  | Engagement with Senior Management Group, including High-Level Task Forces such as that on Global Food Security with the view of ensuring that LDC concerns feature in the agenda of these task forces | Starting from June 2011 | OHRLLS |
|  | Mainstreaming the IPoA into the work programmes of UN Funds, Programmes and specialized agencies | Engagement with ECESA to ensure that LDC concerns feature in the discussions and deliberations of ECESA and the use of existing ECESA Clusters to advance LDC development agenda | Starting from June 2011 up to the mid-term review of the IPoA | OHRLLS |
|  | Mainstreaming the IPoA into the work programmes of the regional commissions and the sub-regional Offices of ECA (five SROs) | Maintain and further strengthen cooperation between OHRLLS, UNCTAD and the Regional Commissions and Sub-Regional Offices, if any, on the implementation of Istanbul Programme of Action | Starting from June 2011 up to the mid-term review of the IPoA | OHRLLS, UNCTAD and the Regional Commissions |
|  |  | Feature LDC development agenda in the discussions within and deliberations of the governing bodies of the Regional Commissions and Sub-Regional Offices of ECA (five SROs) | Starting from June 2011 up to the mid-term review of the IPoA | Regional Commissions (ECA and its SROs, ECLAC, ESCAP and ESCWA) and OHRLLS, |
|  |  | Engagement with the regional consultative mechanisms in different regions to ensure that LDC concerns feature in the discussions and deliberations of this UN-wide Regional Coordination Mechanisms (RCMs) and sub-regional Coordination Mechanisms, if applicable. | Starting from June 2011 up to the mid-term review of the IPoA | ECA, ESCAP, OHRLLS and UNCTAD |
|  | Mainstreaming the IPoA into the work programmes of the BWIs, as appropriate, other international organizations and regional banks | Maintain and further strengthen cooperation between OHRLLS and other international organizations and regional banks on the implementation of the Istanbul Programme of Action | Starting from June 2011 up to the mid-term review of the IPoA | OHRLLS, BWIs, other international organizations and regional banks |
|  | Promoting the contributions of the UN System and those of the BWIs and other international organizations and regional banks in the implementation of the IPoA | Process | Inter-agency brainstorming to take stock of the IPoA and discuss the way forward | End of June 2011 | OHRLLS, IACG, UN organizations and other international organizations |
|  |  |  | Institutionalization of the interagency coordination framework / Annual IACG meeting | Two meetings a year until the mid-term review of the IPoA | OHRLLS, IACG, UN organizations and other international organizations |
|  |  | Substantive Activities | Establish a Task Force to work on the terms of reference for the joint gap and capacity analysis with the aim of establishing a Technology Bank and Science, Technology and Innovation supporting mechanism | Between August 2011-December 2011 | OHRLLS, UNCTAD, UNIDO, UNESCO, World Bank, WTO, WIPO and ITU |
|  |  |  | Task Force to prepare proposals on activities related to the functions of the Science, Technology and Innovation Center | January 2012-March 2012 | OHRLLS, UNCTAD, UNIDO, UNESCO, World Bank, WTO, WIPO, ITU and the Government of Turkey |
|  |  |  | Meetings of Investment Advisory Council (IAC) to advance a number of specific commitments contained in the IPoA, including on concessional start-up finance and investment preference regimes (Aid for Investment) | Two meetings will be held, one in 2012 and another in 2013 | UNCTAD, OHRLLS, the private sector |
|  |  |  | Encourage the Social Protection Floor Advisory Group to substantiate commitments on this subject matter | As determined by the Social Protection Floor Advisory Group | ILO and WHO, together with partner agencies, OHRLLS, WFP, the CEB Secretariat, ECA and ESCAP |
|  | Promoting the contributions of the UN System and those of the BWIs and other international organizations and regional banks in the implementation of the IPoA |  | Establish an inter-agency working group on resource mobilization which will be entrusted with the responsibility of substantiating commitments in the areas of aid, FDI, remittances as well as on domestic resource mobilization | Between October 2011-December 2011 | OHRLLS, UNCTAD, IMF, the World Bank, DESA |
|  |  |  | Partner with the ECESA Cluster on Social Development with the view of involving this Cluster in the substantiation of commitments on human and social development | As determined by the ECE-ESA Cluster on Social Development | DESA/DSPD, OHRLLS, UNFPA, UNICEF, ECA, ESCAP and other members of the Cluster |
|  |  |  | Establish and convene a meeting of an inter- agency working group on the Indicators for the monitoring, follow-up and review of the IPoA | Between June 2011-December 2011 | OHRLLS, DESA, UNCTAD, the UN Statistical Commission, ECA, ESCAP, UNFCCC UNESCO/UIS , UNOPS , OECD, World Bank |
|  |  |  | Establish an inter-agency working group on crisis mitigation and resilience building to substantiate the commitments on this subject matter. These commitments relate, among others, to supporting LDCs’ risk mitigation strategies, facilitating LDCs’ access to required resources from different environment and climate funds, accelerating the legal and institutional arrangements for the establishment of the Green Climate Fund. | Between June 2011-December 2011 | UNDP, the World Bank, OHRLLS, WFP, the CEB Secretariat, UNCTAD , ECA, ESCAP, UNEP, UNFCCC, UNCCD, WMO, Regional Banks and other organizations with large field presence in LDCs |
|  |  |  | Establish an inter-agency working group on agriculture, food security and rural development to substantiate the commitments on this subject matter. | Between June 2011-December 2011 | FAO, IFAD, WFP, ,OHRLLS, the CEB Secretariat and all relevant organizations with field presence in LDCs |
|  |  |  | Partner with UN CEB Inter-Agency Cluster on Trade and Productive Capacity in rolling out trade-related commitments contained in the Istanbul Programme of Action. | As determined by the UN CEB Inter-Agency Cluster on Trade and Productive Capacity | UNCTAD, WTO, OHRLLS, the CEB Secretariat, World Bank, IMF, ITC, UNDP, UN Regional Commissions and UNITAR |
|  |  |  | Organize two capacity-building workshops for the national focal points on the importance of meteorological challenges and services | The first meant for African LDCs will be convened in October 2011, while the second workshop intended for Asian and Pacific LDCs will be held in 2012 | WMO and OHRLLS |
|  |  |  | Continue work of the United Nations Steering Committee on Tourism for Development (SCTD) | As determined by the TOR of the UN Steering Committee on Tourism for Development (SCTD) | UNWTO, ILO, ITC,UNCTAD, UNDP, UNESCO, UNIDO and WTO |
|  |  |  | Prepare the Report of the Secretary General on how to ensure the effective implementation of the functions of OHRLLS and to strengthen is capabilities and its effectiveness | Jun-12 | UN Secretariat |
|  | Follow up, monitoring and review of the Istanbul Programme of Action | Convene the Open Forums on Partnerships to provide platform for UN System Agencies to brief/report on the efforts and initiatives in implementing the IPoA | These forums will be organized in 2012 and 2013 | OHRLLS and UN System Agencies |

|  | Objectives | Activities to be undertaken | Target dates for action | Responsible intergovernmental bodies, agencies and other entities |
| --- | --- | --- | --- | --- |
| South-South Cooperation | Promoting the complementary role of South South Cooperation in the implementation of the IPoA | Engagement of the countries of the South in the implementation of the IPoA | Starting from June 2011 up to the mid-term review of the IPoA | LDCs and member states from the South, UN Funds, Programmes and Agencies, including OHRLLS, UNCTAD, UNDP, UNEP, and the Bretton Woods Institutions. |

|  | Objectives | Activities to be undertaken | Target dates for action | Responsible intergovernmental bodies, agencies and other entities |
| --- | --- | --- | --- | --- |
| Enhanced Partnerships with Parliaments, Private Sector and Civil Society | Promoting the contribution of LDC and non LDC parliaments to the implementation of the 2011 – 2020 Istanbul Programme of Action for the Least Developed Countries | Project Proposal with IPU to be finalized and MOU to be signed | June-July 2011 | IPU and OHRLLS |
|  |  | Seek funding for the project in cooperation with IPU | July 2011-September 2011 | IPU and OHRLLS |
|  |  | Global follow up of the IPoA – organization of global follow up meeting to the 2011 Parliamentary Forum (2012) | July 2011 - December 2013 | IPU and OHRLLS |
|  |  | Liaise with the UNDP to setup UN focal points at national level to strengthen the parliamentary focal point mechanism at the national level | July 2011 - December 2012 | IPU and OHRLLS, UNDG/Country Resident Coordinators |
|  |  | Support parliamentary structures and capacity building by organizing national and regional workshops in cooperation with UNDP and IPU | January 2012 - December 2015 | IPU and OHRLLS |
|  |  | Build a gateway of information, e.g. brochure, booklet, fact sheets on “integrating the IPOA into national development plans and the role of parliaments” to enhance parliaments awareness of and access to information on the IPOA and the LDC development process | July 2011 - December 2015 | IPU and OHRLLS |
|  |  | Undertake advocacy work to promote the role of the UN system in supporting parliaments to fulfil their role in the implementation of the Programme of Action | July 2011 - December 2015 | IPU and OHRLLS |
|  |  | Explore other ways of support the LDC and non LDC parliaments in the implementation of the IPoA | July 2011 - December 2015 | IPU and OHRLLS |
|  | Promoting private sector's contribution to the implementation of the Istanbul Programme of Action | Convene a wrap-up meeting with the private sector steering committee to reflect on the outcomes of the Conference and discuss possible ways the private sector can continue to contribute to the process. | Jun-11 | OHRLLS |
|  |  | Develop a strategy of a channels/platform for a continued engagement of the private sector in the implementation, follow-up, monitoring and review of the Istanbul Programme of Action | July 2011-September 2011 | OHRLLS, UNCTAD and the Private Sector |
|  |  | Establish a "Business Advisory Committee” | Last quarter 2011 | OHRLLS, UNCTAD and the Private Sector |
|  |  | Convene the Global Business Forum for the development of the least developed countries | Sep-12 | OHRLLS , UNCTAD, ITC, World Bank, Global Compact |
|  | Promoting civil society’s contribution to the implementation of the Istanbul Programme of Action | Convene a civil society steering committee meeting to reflect on the outcomes of the Conference | Jun-11 | OHRLLS, NGLS |
|  |  | Develop in consultation with NGLS CSO strategy to engage CSOs implementation of IPoA | Jul-11 | OHRLLS, NGLS and the Civil Society |
|  |  | Establish CSO Advisory Committee on the LDCs | August/September 2011 | OHRLLS, NGLS and the Civil Society |
|  |  | Convene first meeting of CSO Committee on the LDCs | Oct-11 | OHRLLS, NGLS and the Civil Society |
|  |  | Convene a regional Civil Society Forum in Africa and Asia in the context of the regional review of the implementation of the IPoA | Mid-2012 | OHRLLS, NGLS and the Civil Society |
|  |  | Involvement of the civil society in the implementation, monitoring and follow-up of the Istanbul Programme of Action | September 2011-2015 | OHRLLS, NGLS and the Civil Society |
|  | Promoting the contribution of the academia and philanthropic foundations into the implementation of the IPoA | Develop strategy to engage academic and philanthropic foundations in the implementation of the IPoA | Jul-12 | OHRLLS, UN Women in consultation with academic and philanthropic foundations |
|  |  | Implementation of strategy, which may include quarterly roundtables at new York/Washington-based institutions, | Starting from September 2011 | OHRLLS, academic and philanthropic foundations |
|  |  | initiate students (developed countries and LDCs) to work on joint projects focusing on LDCs |  |  |

|  | Objectives | Activities to be undertaken | Target dates for action | Responsible intergovernmental bodies, agencies and other entities |
| --- | --- | --- | --- | --- |
| Advocacy and Awareness-Raising | Ensuring greater awareness about the IPoA | Develop draft advocacy and outreach strategy (internal) | Between June - August 2011 | OHRLLS, DPI |
|  |  | Disseminate draft advocacy and outreach strategy to LDCs for input | Sep-11 | OHRLLS |
|  |  | Finalize advocacy and outreach strategy | October 2011-December 2011 | OHRLLS |
|  |  | Consult with Member States for funding for advocacy and outreach strategy, including discussion on global campaign for LDCs | Between September 2011 and November 2011 | OHRLLS |
|  |  | Initiate implementation of advocacy and outreach strategy | October 2011-December 2011 | OHRLLS |
|  |  | Initiate and prepare outline of UN Communication Cluster on LDCs (TOR) | Sep-11 | OHRLLS |
|  |  | Convene first meeting of UN Communication Cluster (HQ) | Nov-11 | OHRLLS, DPI |
|  |  | Convene first meeting of UN Communication Cluster (Regional) | Jan-12 | OHRLLS, DPI and regional economic commissions |
|  |  | Develop proposal for UN International Day for the LDCs | Jul-11 | OHRLLS |
|  |  | Identify ‘Goodwill Ambassador’ for the LDCs with support from SG’s Goodwill Ambassador Office | Sep-11 | OHRLLS |
|  |  | Convene first meeting with Goodwill Ambassador | Nov-11 | OHRLLS |
|  |  | Prepare outline of documentary video outlining ‘Best Practices in LDCs’ | September-November 2011 | OHRLLS |
|  |  | Prepare publications including comprehensive communication kit on each of the priority areas of IPoA | September-November 2011 | OHRLLS |
|  |  | Visit of the High Representative to Key capitals of the Development Partners of LDCs (Countries TBD) | June 2011 - December 2011 | OHRLLS, Host Country |
|  |  | Participation of the High Representative in meetings of Key international and Regional Organizations such as the World Bank, IMF, (UNCTAD XIII, ESCAP, ECA, UNIDO, WTO, African Union, etc. to raise awareness of the IPoA and emphasize implementation | June 2011- April 2012 | OHRLLS |
|  |  | Engagement of the Eminent Person Group in advocacy activities | Starting from June 2011 up to the mid-term review of the IPoA | OHRLLS |

|  | Objectives | Activities to be undertaken | Target dates for action | Responsible intergovernmental bodies, agencies and other entities |
| --- | --- | --- | --- | --- |
| Resource Mobilization | Mobilizing resources in support of the implementation of the Istanbul Programme of Action | Develop a strategy for resource mobilization | Between June 2011-September 2011 | OHRLLS |
|  |  | Preparation of project proposals with a view to solicit extrabudgetary funds in support of the implementation of the IPoA and the activities spelled out in the Road Map | Ongoing | OHRLLS |
|  |  | Implementation of the projects funded by donors | Starting from October 2011 up to the mid-term review of the IPoA | OHRLLS |
|  |  | Activities in preparation of the establishment of the establishment of the International Migrants Remittance Observatory | Between June 2011-December 2011 | OHRLLS |
|  |  | Explore the possibility of establishing a Multi-Donor Trust Fund for Tourism for Development | July 2011 - December 2015 and beyond | UNWTO, ILO, ITC,UNCTAD, UNDP, UNESCO, UNIDO and WTO |