Assumptions:

- This is a guiding/living document which will be considered “preliminary” until the end of the third cycle in 2025

- DOALOS calendar remains largely similar to previous years

- Approximately two AHWGW meetings per year (simulated here as March and early September every year)

- Experts will have limited capacity to work during the winter and summer holidays (have added buffers, tried to avoid scheduling important meetings during this time)

- Lessons learned and evaluation process for GOE and secretariat is continuous: Notes are taken throughout the third cycle to ensure that documentation exists once lessons learned process begins

- Remaining members of GOE will be appointed in due course (As of March 2022 - GOE still partially constituted: 21/25)

- In-person meetings and workshops continue to pose challenges in 2022 due to the impacts of the COVID-19 pandemic. It is also yet to be seen whether they will be possible in 2022/2023

Not added here:

- Some GOE teleconferences (approx. bimonthly, or more frequent if needed)

- Bureau meetings

- Intergovernmental meetings (at least 15) (except for those identified for 2022) e.g.:

  - UNFCCC (SBSTA Q2 and COP Q4 every year)

  - UNEA (month varies) roughly every two years

  - IOC-UNESCO Assembly (June/July every year) and

  - any open UN Decades workshops, etc.

  - IPBES plenary (Q1 or Q2 every year)

  - BBNJ IGC sessions

- Briefings (5) and side events (8) in margins of relevant intergovernmental meetings and major Conferences

- Possible Teleconferences with NFPs and IFPs

- Fundraising for voluntary trust fund and special scholarship fund

- Pre- and post-workshop work, including evaluations

- Any actions necessary to implement outreach and engagement strategy, including the compilation and maintenance of CB inventory, the maintenance of RP website and the development of the French version of the RP website, as well as outreach campaigns.

Colour coding:

| Secretariat | NFPs |
| --- | --- |
| GOE | Holiday season |
| AHWGW | WOA II |
| Bureau | CB |
| GA | Conveners of writing teams |
| Intergovernmental meetings |  |

| Date | Body/output | Posible event/process | Comments |
| --- | --- | --- | --- |
| 2020 |  |  |  |
| 09-10 September 2020 | AHWGW | 13th meeting of AHWGW | AHWGW considers lessons learned from 2nd cycle, POW and RR for 3rd cycle. |
| 06 November 2020 | AHWGW | 14th meeting of AHWGW | AHWGW considers submission of WOA II to GA |
| Nov-20 | General Assembly | Second round of omnibus resolution ICs |  |
| 31 December 2020 | General Assembly | Omnibus resolution is adopted. GA welcomes WOA II. RP budget is approved. | https://undocs.org/en/A/RES/75/239 |
| Late Dec-20 to Early Jan-21 | Holiday season |  |  |
| 2021 |  |  |  |
| Jan/Feb-21 | Secretariat | - Secretariat sends call for nominations for the GOE of the third cycle. - Planning for the new cycle: how/when to implement programme of work - Work related to budget (release of funds, etc.) | This took place on 19 January 2021, with a deadline of 28 February 2021. |
| Mar-21 | Secretariat | - Reminders to the Groups of Latin American and Caribbean States, African States and the Eastern European States to nominate experts to the GOE | New deadline of 16 April 2021 given. |
| Apr-21 | Secretariat | - Welcome new GOE members and produce confirmation letters - Start search for consultant for outreach and engagement strategy - Launch of WOA II | Launch of WOA II took place on 21 April 2021 |
| April-21 | Bureau | - Approval given for GOE to begin work while awaiting additional nominees |  |
| May-21 | GOE | - First GOE meetings - Agree on Joint Coordinators + Deputies - Consultations regarding working methods and procedures - Agreement on structure of SharePoint folders and updates - Start work on TORs and working methods doc - Prepare for AHWGW in June: Mechanism for 3rd cycle POE, TORs for NFPs and IFPs. | First GOE meetings took place on 11 and 14 May 2021. |
| May-21 | Secretariat | - Support GOE in organizing its work - Establish GOE SharePoint - Intro to RP/welcome - Preparing the draft preliminary timetable and implementation plan for the third cycle - Support Bureau in organizing its work - Interviews for consultant for outreach and engagement strategy |  |
| June-21 | Secretariat | - Send docs for AHWGW meeting and inform GOE of the dates - Evaluate POE and GOE databases |  |
| June-21 | GOE | - Second and third GOE meeting - Agreement on conference calls procedure/timing - Consideration of and potential appointment of further Deputies - Start discussions on scoping exercise for brief documents, agree on procedure, and begin development of the outline - Finalization of the Terms of Reference (TOR) of the Group of Experts (GOE) for the third cycle |  |
| June-21 | 8th Session of the Plenary of the Intergovernmental Science-Policy Platform on Biodiversity and Ecosystem Services (IPBES-8) |  | Virtual |
| 14 Jul-28 Sep ‘21 | AHWGW | 15th meeting of AHWGW | AHWGW to approve: - GOE TORs and working methods - TORs for NFPs and IFPs - Mechanism for establishing POE - Draft recommendations to the GA |
| Jul-Sep ‘21 | GOE | - Drafting of the 4 brief documents to begin in consultation with relevant IGOs - Completing the summary/compilation of all the comments received on the brief documents |  |
| Mid to late Sep-21 | General Assembly | GA High level week |  |
| Oct-21 | Secretariat | - Planning of regional CB workshops to begin - Support GOE and Bureau - Invite appointment and/or extension of NFPs - Invite appointment of IFPs - Organization and follow-up to AHWGW 15 - Planning of CB programme: inviting potential partners, discussions etc. - Support for GOE meeting - Implementation of scoping exercise for the 4 brief documents. - Selection of a consultant for and development of the outreach and engagement strategy - Contact previous POE to ascertain interest in continuing serving |  |
| Oct-21 | GOE | Virtual meeting: - To agree on the solutions/responses to the comments received from IGOs on the 4 brief documents. - Start discussions on: - CB programme details - Outreach and engagement strategy |  |
| Oct-21 | Bureau | Bureau meeting to discuss the progress of 3rd cycle preparation |  |
| Oct-21 | General Assembly | First round of omnibus resolution ICs |  |
| 31 Oct-12 Nov 21 | UN Climate Change Conference 2021 (COP26) in Glasgow, UK |  | In-person |
| May-21 | Secretariat | WOA II is published in all six languages. |  |
| Nov-21 | GOE | Completion of the first draft of all the brief documents, including all the comments |  |
| Nov-21 | General Assembly | Second round of omnibus resolution ICs |  |
| 1-Dec-21 | GOE | Review of all the brief documents, with support from the Secretariat |  |
| 9-Dec-21 | General Assembly | Omnibus resolution is adopted |  |
| Late Dec-21 – mid Jan-22 | Holiday season |  |  |
| 2022 |  |  |  |
| Jan-22 | GOE | Virtual meeting: - Finalization of the brief documents on WOA II - Working methods in a virtual environment. - GOE/RP participation in other ocean-related processes. - Updates on the outreach and engagement strategy - Regional workshops |  |
| Jan-22 | Secretariat | - Editing of 4 brief documents - Support with the preparation of the preliminary timetable and implementation plan for the third cycle - Sending a call seeking hosts for the regional workshops on CB and on the Assessment(s) |  |
| Feb-22 | GOE | Virtual meeting: - Preliminary scope of the next assessment(s) and preparation of the concept note - Preliminary annotated outline for the assessment(s) - Preliminary draft agenda for the 5 regional workshops to support the preparation of the assessment(s) |  |
| 9-11 February ‘22 | One Ocean Summit |  | Hybrid, Brest, France |
| End of Feb ’22 (TBC) | Bureau | Virtual meeting: - Brief documents on WOA II - Preliminary timetable and implementation plan for the third cycle - Planning of the 16th AHWGW - Presentation of the outreach and engagement strategy |  |
| End Feb-March ’22 (TBC) | 16th AHWGW | To approve the: - 4 brief documents on WOA II; - Preliminary timetable for the third cycle of the Regular Process (2021-2025) | Via correspondence |
| 1 – 3 March ‘22 | The Economist 9th Annual World Ocean Summit & Expo |  | Hybrid, Lisbon, Portugal |
| 7-18 March ‘22 | Fourth session of the Intergovernmental Conference on BBNJ |  | In-person (delegations), New York, USA |
| March-22 (TBD) | Secretariat | - Send out a call for written input on the concept note on the scope of the assessment(s) - Evaluation, enhancement and maintenance of the database of recent and ongoing global and regional assessments |  |
| Mar-22 | Bureau | Virtual meeting: - Concept note on the scoping of the next Assessment(s) - Tentative schedule and draft agendas for the first round of the 5 regional workshops to support the preparation of the assessment(s) - Update on the preparations for the 3 regional workshops on capacity-building |  |
| 13-14 April | 7th Our Ocean Conference |  | In-person, Palau |
| April-22 (TBC) | Assessment(s) | First round of the regional workshop for scoping the assessment(s): Workshop I | Virtual or Hybrid |
| April-May ’22 (TBD) | GOE | First in-person meeting in New York *Agenda to be agreed |  |
| 25 April-8 May ‘22 (TBC probably in the third quarter of 2022) | UN Biodiversity Conference (CBD COP 15 – Part 2) |  | In person (delegations), Kunming, China |
| May ‘22 | Secretariat | The 4 brief documents on WOA II are translated in all UN official languages | The printing date of the 4 brief documents will be decided once the translation is completed. |
| May-22 (TBC) | Assessment(s) | First round of the regional workshop for scoping the assessment(s): Workshop II | Virtual or Hybrid |
| 14-20 May | Blue Climate Summit |  | In-person |
| 8 June ‘22 | UN World Oceans Day |  |  |
| Jun-22 | GOE | Virtual meeting: - Update on the 2 regional workshops held on scoping the assessment(s) - Update on the preliminary scope of the assessment(s) and annotated outline for the assessment(s) - Guidelines for the composition of writing teams - Guidelines for the identification of peer reviewers - Modalities for the review process (peer-reviewers, secretariat, IGOs) - Identification of potential members of writing teams | Preliminary annotated outline to include a list of specific expertise needed for each topic to be addressed |
| Jun-22 | Secretariat | - Inviting nominations and recommendations of additional experts to the Pool of Experts for the third cycle upon the completion of the first draft of the annotated outline of the assessment(s) |  |
| Jun-22 (TBD) | CB | Capacity-building Workshop: Workshop I | Virtual or Hybrid |
| Jun-22 (TBD) | Assessment(s) | First round of the regional workshop for scoping the assessment(s): Workshop III | Virtual or Hybrid |
| 27 June-1 July ‘22 | UN Ocean Conference in Lisbon, Portugal |  | In-person |
| 3-9 July ‘22 | 9th Session of the Plenary of the Intergovernmental Science-Policy Platform on Biodiversity and Ecosystem Services (IPBES-9) |  | In-person (delegations), Bonn Germany |
| Jul-22 | Secretariat | Start planning the 17th AHWGW |  |
| Aug-22 | Bureau | Virtual meeting: - Update on the [3] regional workshops held on the assessment(s) - Update on the preliminary scope of the assessment and annotated outline for the assessment(s) - Guidelines for the composition of writing teams - Guidelines for the identification of peer reviewers - Modalities for the first stage of the review process (peer-reviewers, secretariat and IGOs) |  |
| Aug-22 | Secretariat | Circulate documents for 17th AHWGW |  |
| Aug-22 (TBC) | CB | Capacity-building Workshop: Workshop II | Virtual or Hybrid |
| Aug-22 (TBC) | Assessment(s) | First round of the regional workshop for scoping the assessment(s): Workshop IV | Virtual or Hybrid |
| 5-9 September ‘22 | 35th Committee on Fisheries of the FAO (COFI-35) |  | In-person (delegations), Rome, Italy |
| Sep-22 (TBC) | AHWGW | 17th meeting of AHWGW: - Progress on the Regional Workshops for the Assessment(s) and those on capacity-building - Update on the preliminary scope of the assessment(s) and annotated outline for the assessment(s) - Guidelines for the composition of writing teams - Guidelines for the identification of peer reviewers - Modalities for the review process (peer-reviewers, secretariat, IGOs) |  |
| Early Sep-22 | Secretariat | - Send calls for offers to host regional workshops for developing the assessment(s) in 2023 right after AHWGW meeting. |  |
| Mid to late Sep-22 | General Assembly | GA High-level week |  |
| Late Sep-22 | General Assembly | Informal consultations on the draft resolution on Oceans and the law of the sea: first round |  |
| Oct-22 | Assessment(s) | First round of the regional workshop for scoping the assessment(s): Workshop V | Hybrid or Virtual |
| Oct-22 | CB | Capacity-building Workshop: Workshop III | In-person |
| 7-18 Nov ‘22 | UN Climate Change Conference 2022 (COP 27) |  | In-person, Sharm El-Sheikh, Egypt |
| Nov-22 | GOE | Virtual meeting: - Finalization of the scope of the assessment(s) *(outputs of the workshops are synthesised and commonalities in priorities identified) - Based on assessment prioritisation process develop an annotated outline for the assessment(s) - Identification of potential members of writing teams |  |
| Nov-22 | General Assembly | Informal consultations on the draft resolution on Oceans and the law of the sea: second round |  |
| Dec-22 | General Assembly | Omnibus resolution is adopted |  |
| Late Dec-22 – mid Jan-23 | Holiday season |  |  |
| 2023 |  |  |  |
| Jan-23 | GOE | - Finalize the proposed scope of the assessment(s), associated comprehensive annotated outline(s) containing a summary of content and format a list of expertise needed for the writing teams, and an assessment of potential gaps and overlaps in expertise and the way to manage them - Identification of potential members of writing teams - Develop guidelines for writing teams |  |
| Jan-23 | Secretariat | - Prepare documents for the 18th AHWGW |  |
| Feb-23 | Bureau | - Update on the proposed scope of the assessment(s), a comprehensive annotated outline containing a summary of content and format, a list of expertise needed for the writing teams, and an assessment of potential gaps and overlaps and the way to manage them |  |
| Feb-23 | Secretariat | Circulate documents for 18th meeting of AHWGW |  |
| Mar-23 | AHWGW | 18th meeting of AHWGW - Approve the proposed scope of the assessment(s); a comprehensive annotated outline containing a summary of content and format; a list of expertise needed for the writing teams; and an assessment of potential gaps and overlaps in expertise and the way to manage them. |  |
| Late Mar-23 | GOE | - Finalize lists of writing teams and peer-reviewers *(additional experts can also be added later on) - Finalize guidelines for writing teams | In-person |
| Apr-23 | Bureau | - Approve list of writing teams - Approve list of peer reviewers |  |
| Apr-23 | Secretariat | - Send letters to members confirming establishment of writing teams - Establish line of communication between GOE and writing teams Prepare for second round of 5 regional workshops in support of drafting of the Assessment(s) - Prepare for the 2 regional workshops on CB and international symposium on capacity-building |  |
| Apr-23 (TBD) | CB | Capacity-building Workshop: Workshop IV | Hybrid or Virtual |
| May-23 | Conveners of writing teams | - In-person meeting to discuss annotated outlines, gaps/overlaps and agree on writing assignments - Commence the drafting of assessment(s) | Conveners and members of writing teams to hold virtual meetings throughout drafting period - March 2024 (TBC) |
| Jun-23 (TBD) | Assessment(s) | Second round of the regional workshop for drafting of the assessment(s): Workshop I |  |
| Jun-23 (TBD) | CB | Capacity-building Workshop: Workshop V | Hybrid or Virtual |
| Jul-23 | Secretariat | Prepare documents for 19th AHWGW - Updates on the establishment of writing teams - Update on the drafting arrangements - Update on peer-reviewers - Update on regional workshops - Update on capacity-building - Other mid-point updates |  |
| Jul-23 (TBD) | Assessment(s) | Second round of the regional workshop for drafting the assessment(s): Workshop II |  |
| Aug-23 | Bureau | Consider documents for the 19th AHWGW |  |
| Aug-23 | Secretariat | Circulate documents for the 19th AHWGW |  |
| Aug-23 (TBD) | Assessment(s) | Second round of the regional workshop for drafting the assessment(s): Workshop II |  |
| Early Sep-23 | CB | International symposium - a focused and interactive knowledge-sharing event drawing upon the outcomes of the 5 regional workshops held in 2022 and 2023 | Hybrid or Virtual: Two-day Could be back-to-back with the 19th AHWGW |
| Early Sep-23 | AHWGW | 19th meeting of AHWGW - Updates on the establishment of writing teams - Update on the drafting arrangement - Update on peer-reviewers - Update on regional workshops - Update on capacity-building Other mid-point updates |  |
| Early Sep-23 | GOE | In-person meeting to discuss: - Progress in the preparation of the Assessment(s) - Etc. | Could coincide with 19th meeting of AHWGW and the international symposium for capacity-building |
| Mid to late Sep-23 | General Assembly | GA High-level week |  |
| Sep-23 | Secretariat | Convenes a one-day inter-agency meeting in conjunction with the General Assembly |  |
| Oct-23 | Assessment(s) | Second round of the regional workshop for drafting the assessment(s): Workshop IV |  |
| Oct-23 | General Assembly | Informal consultations on the draft resolution on Oceans and the law of the sea: first round |  |
| Nov-23 | Assessment(s) | Second round of the regional workshop for drafting the assessment(s): Workshop V |  |
| Nov-23 | General Assembly | Informal consultations on the draft resolution on Oceans and the law of the sea: second round |  |
| Dec-23 | General Assembly | Omnibus resolution is adopted |  |
| Late Dec-23 – mid Jan-24 | Holiday season |  |  |
| 2024 |  |  |  |
| Jan-24 | Secretariat | Prepare docs for the 20th meeting of AHWGW - Modalities for the second stage of the review process (States) |  |
| Feb-24 | Bureau | Consider docs for 20th meeting of AHWGW: - Modalities for the second stage of the review process (States) |  |
| Feb-24 | Secretariat | Circulate documents for the 20th meeting of AHWGW |  |
| Mar-24 | AHWGW | 20th meeting of AHWGW - Update on the progress in the preparation of the assessment(s) - Approve modalities for the second stage of the review process (States) |  |
| Mar-24 | GOE | In-person meeting to finalize drafts for peer-review | Could coincide with 20th AHWGW |
| March to May-24 | Assessment(s) | First stage of review process: parallel reviews by peer-reviewers, the secretariat and IGOs | Eight weeks |
| March to May-24 | Secretariat | Facilitate the communication of comments to writing teams |  |
| Jun to Jul-24 | Assessment(s) | Writing teams consider review comments and produce proposed responses to peer-review. | Eight weeks |
| Jul-24 | Conveners of writing teams | In-person meeting to discuss reviews, cross-cutting issues and finalise drafts | Remote participation will also be provided. |
| Jul-24 | Secretariat | Prepare docs for 21st meeting of AHWGW - Update on progress in the preparation of the assessment(s) - Process for lessons learned - Planning for the fourth cycle |  |
| Jul to Aug-24 | GOE | Consider review comments and proposed responses from the writing teams | Three weeks |
| Aug-24 | Bureau | Consider docs for 21st meeting of AHWGW: - Update on progress in the preparation of the assessment(s) - Process for lessons learned - Planning for the fourth cycle |  |
| Aug-24 | Secretariat | Circulate docs for 21st meeting of AHWGW |  |
| Early Sep-24 | AHWGW | 21st meeting of AHWGW - Update on progress in the preparation of the assessment(s) - Process for lessons learned - Planning for the fourth cycle |  |
| Early Sep-24 | GOE | Meeting to revise the draft chapters of the assessment(s), considering the comments of writing teams, and finalize the first draft of the Assessment(s) | Could coincide with 21st meeting of AHWGW |
| Sep-24 | Secretariat | Consolidate and format draft chapters |  |
| Sep/Oct-24 | Assessment(s) | Copyediting of the first draft of the Assessment(s) | Four to Eight weeks. At least one consultant needed |
| Mid to late Sep-24 | General Assembly | GA High-level week |  |
| Oct/Nov-24 | Assessment(s) | States review the first draft of the Assessment(s) | Six weeks |
| Oct-24 | General Assembly | Informal consultations on the draft resolution on Oceans and the law of the sea: first round |  |
| Nov-24 | General Assembly | Informal consultations on the draft resolution on Oceans and the law of the sea: second round |  |
| Nov/Dec-24 | Secretariat | Consolidate States comments and sent to respective writing teams |  |
| Dec-24 | General Assembly | Omnibus resolution is adopted |  |
| Late Dec-24 – mid Jan-25 | Holiday season |  |  |
| 2025 |  |  |  |
| Jan to Feb-25 | Assessment(s) | Writing teams review States’ comments and produce proposed responses. | Four weeks |
| Jan to Feb-25 | Secretariat | Commence lessons learned exercise from the third cycle - Compiles its lessons learned from the third cycle into one document - Drafts questions based on its lessons learned for States, IGOs, etc. - Invites States, IGOs, GOE to provide their lessons learned |  |
| Feb to Mar-25 | GOE | Review comments and proposed response to States’ comments, and finalize the second draft of the Assessment(s) in the light of comments from States and proposed responses from writing teams and presents it to the Bureau |  |
| Mar-25 | Bureau | Receive oral briefings by GOE on the second draft of the Assessment(s) | Bureau meeting to coincide with the last day of the meeting of the GOE |
| Mar to Apr-25 | Secretariat | - Format the second draft of the Assessment(s) and circulate it for States’ final review, together with agreed responses by GOE to States’ comments - Work on draft programme of work for the fourth cycle - Work on the preliminary resource requirements for the fourth cycle |  |
| May-25 | Assessment(s) | Exchanges between Bureau and GOE on questions arising from the Assessment(s), resolving outstanding issues through exchanges between States’ representatives and the GOE |  |
| May-25 | GOE | - Finalize the Assessment(s) - Conduct lessons learned exercise |  |
| May-25 | Bureau | Receive oral reports by GOE on changes made to the second draft as a result of States’ review, and approves the submission of the Assessment(s) to AHWGW | Bureau meeting to coincide with the in-person meeting of the GOE |
| May-25 | Assessment(s) | Final editing of the Assessment(s) | Four weeks One consultant copyeditor |
| May-25 | Secretariat | Finalize draft lessons learned from the third cycle, as well as draft programme of work and preliminary resource requirement for fourth cycle |  |
| Jun-25 | Assessment(s) | Unedited version of the Assessment(s) (TBD) and executive summary/ies are sent for translation | 8 weeks before preparatory period for AHWGW begins. May need to be adjusted to 10 weeks. |
| Jun-25 | GOE | Review and provide input on lessons learned from the third cycle, as well as draft programme of work and resource requirement for the fourth cycle |  |
| Jul-25 | Secretariat | Prepare other documents for 22nd meeting of AHWGW, besides lessons learned, draft programme of work and preliminary resources requirement |  |
| Jul-25 | Bureau | Consider and approve the submission of the finalize assessment(s), lessons learned from the third cycle, programme of work and resource requirement for the fourth cycle to AHWGW |  |
| Jul-25 | Secretariat | Circulate documents for the 22nd meeting of AHWGW: - Executive summary/ies of the Assessment(s) in all six official languages, along with the advance, unedited version of the Assessment(s) in English only - Lessons learned from the third cycle - Draft programme of work for the fourth cycle - Preliminary resource requirement for the fourth cycle |  |
| Mid to late Sep-25 | General Assembly | GA High-level week |  |
| Oct-25 | AHWGW | 22nd meeting of AHWGW: - Consider and authorize the submission of the Assessment(s) to GA - Consider and endorse the programme of work and resource requirement for the fourth cycle |  |
| Oct-25 | General Assembly | Informal consultations on the draft resolution on Oceans and the law of the sea: first round |  |
| Nov-25 | General Assembly | Informal consultations on the draft resolution on Oceans and the law of the sea: second round |  |
| Dec-25 | General Assembly | Omnibus resolution is adopted |  |
| Dec-25 | Assessment(s) | - Translated Assessment(s) available in all six official languages - Desktop publishing of assessments begins | Six weeks with one consultant for desktop publishing |
| Dec-25 | Secretariat | - Digital versions of the Assessment(s) in all six official languages to be prepared |  |
| Late Dec-25 to mid- Jan 26 | Holiday season |  |  |
| 2026 |  |  |  |
| Jan-26 | Secretariat | Printing of the Assessment(s) in all UN official languages. |  |